## Slide 1: ABC123 dose-finding strategy
Program BX-401, CD20xCD3 T-cell engager · Indication relapsed follicular lymphoma · Stage end of escalation, entering expansion
Revised 2026-09-11 · Next revision ?
Phase 1b key objectives: Characterize safety, PK, PD and preliminary activity across the dose range. Identify a dose that safely depletes in tissue.
Phase 2b key objectives: Evaluate a dose that leads to close to 100% target cell depletion. Also evaluate a dose with less depletion, in case safety is improved without compromising efficacy.
Dose decisions
Decision | Position and evidence | State | Team | Needed for
Stop escalation | Stop at 120 mg or at a depletion plateau Exposure-response on B-cell depletion and response rate | ◐ Provisional | ⚠️ Split: disease team wants 240 mg explored | Phase 1 at the 120 mg cohort
Expansion criteria | Expand a dose with near-complete peripheral B-cell depletion and manageable CRS; 30 and 120 mg qualify Escalation PK and depletion; expansion slots are the constraint | ◐ Provisional | ✅ Agreed | Phase 1 expansion Nov 2026
Number of Phase 2b doses | 2 full doses, randomized against each other Project Optimus expects a randomized comparison of more than one dose | ◐ Provisional | ✅ Agreed | Phase 2b protocol Q1 2027
Which Phase 2b doses | One near complete depletion, one lower; TBD among 30, 60, 120 mg ⏰ Expansion exposure-response at the Q3 2027 interim | ○ Open | – Not asked | Phase 2b protocol Q1 2027
Legend ○ Open ◐ Provisional ● Locked · ✅ Agreed ⚠️ Split – Not asked · ⏰ evidence lands after the milestone it is needed for

## Slide 2: Regimen decisions
Decision | Position and evidence | State | Team | Needed for
Step-up levels | 0.5 / 3 / 15 mg ⏰ CRS by step, cohorts 1–6; reads out Feb 2027 | ● Locked (~3 mo to amend) | ⚠️ Split: Translational wants 2 steps | Phase 2b protocol Q1 2027
Premedication | Dexamethasone before each step-up ⏰ Pooled CRS by premed use; not randomized, so confounded | ◐ Provisional | ⚠️ Split: Safety wants it before full doses too | Phase 2b protocol Q1 2027
Monitoring | Overnight after each step-up CRS onset times from expansion | ◐ Provisional | – Not asked | Phase 2b protocol Q1 2027
Re-priming after a gap | Restart full step-up after >6 weeks missed ⏰ Class precedent only; no program data planned | ○ Open | – Not asked | Phase 2b protocol Q1 2027
Full-dose interval | Q2W after cycle 3 ⏰ PK simulation only; no program data on Q2W | ○ Open | – Not asked | Phase 2b protocol Q1 2027
Maintenance | None assumed ⏰ Nothing planned that would answer it | ○ Open | ⚠️ Split: Late Dev assumes maintenance in the Ph3 plan | Phase 3 protocol 2028
Legend ○ Open ◐ Provisional ● Locked · ✅ Agreed ⚠️ Split – Not asked · ⏰ evidence lands after the milestone it is needed for
Settled. Starting dose 0.5 mg, MABEL-derived · subcutaneous fixed dose · 3 step-up doses · 7 days between step-ups and to the first full dose. All locked at protocol v1, 2025-03.

## Slide 3: Phase 2b doses, escalation rules and milestones
Phase 2b doses
How many: 2, randomized Which: TBD among Low, Mid, High
LOW
30 mg
~0.4× exposure
Lower end of the effective range; no overnight stay
MID
60 mg
~0.7× exposure
Intermediate; not yet given to any patient
HIGH
120 mg
reference
Near-complete depletion; characterized in expansion
Why this number and spread. One dose near complete depletion and one that depletes less, in case safety improves without losing efficacy. Three-fold apart in exposure is enough for exposure-response. Low with High, unless the Q3 2027 interim shows Low short of adequate activity.
Escalate, expand, stop
↑
Escalate when safety over 21 days is acceptable, CRS is manageable with current premedication, exposure is below target, and B-cell depletion is incomplete.
→
Expand when the dose is in a plausible therapeutic range and the next decision needs more patients, not more dose levels.
■
Stop escalating when depletion is complete and sustained, response rate has plateaued with exposure, or toxicity exceeds the protocol limit. No MTD is needed.
Protocol
2025-03 ✓
Escalation
per cohort
Phase 1 expansion
Nov 2026
Phase 2b protocol
Q1 2027
Phase 3 protocol
2028
Submission
regimen
⏰ Critical path. Which Phase 2b doses is needed in Q1 2027; its evidence arrives Q3 2027. Full-dose interval and re-priming have no planned evidence and will be decided on prior information.